### PhD Research Plan: Bayesian Approach for the Design of Fluid Viscous Dampers for Offshore Wind Turbines

#### 1. Research Overview and Objectives

This PhD research aims to develop an advanced design procedure for fluid viscous damping systems (FVDs) used in offshore wind turbines, with a focus on environmental effects such as temperature fluctuations, wind, and wave loads. The project has three main objectives:

- Addressing temperature effects on FVDs: Offshore wind turbines are exposed to extreme environmental conditions, including fluctuating temperatures. These changes can affect the performance of the fluid inside viscous dampers. I aim to study the behaviour of FVDs under varying environmental loads to enhance their reliability in offshore conditions.

- Applying Bayesian statistics to update theoretical models: Offshore environments present many uncertainties, including those associated with wave and wind loads and temperature fluctuations. Bayesian statistical methods will allow me to update the performance models of FVDs, incorporating real-world data and accounting for the inherent uncertainties in environmental loads.

- Conducting multi-physics simulations using COMSOL or/and ABAQUS or/and ANSYS: By integrating fluid-temperature-structure interactions in multi-physics simulations, I will assess damper behaviour under combined environmental loads. These simulations will be critical for refining the design procedures of FVDs in offshore wind turbines.

The combination of Bayesian statistical updating and multi-physics simulations will lead to a design procedure that enables the consideration of the effect of temperature change in FVDs on the output force from the FVDs for the design of FVDs to be used in offshore wind turbines.

#### 2. Timeline and Milestones

0-2 Months: Understanding Background

During the first two months, I will lay the groundwork for my research by immersing myself in relevant literature and engaging with my supervisory team.

- Conducting an in-depth literature review: I will explore the current state of offshore wind turbine design, the use of dampers in civil engineering, and established methodologies for handling environmental loads. A specific focus will be on the literature regarding temperature effects on damping fluids and the use of Bayesian statistics in performance modelling. I will examine foundational papers, such as those by Black et al. (2003), which apply Bayesian updating to FVD.

- Engaging with supervisors: I will have initial meetings with my supervisory team—Dr. Shoma Kitayama, Dr. Marianna Ercolino, and Dr. Sotirios Argyroudis—to outline expectations, project deliverables, and timelines. Their guidance will help shape the scope of the research and clarify the main goals for each stage.

- Identifying key research questions: My early discussions and literature review will focus on refining the key questions that will drive the research, such as: How does the output force of FVDs vary with temperature fluctuations of silicon fluid due to changes in external temperature and continuous internal interactions between the silicone fluid and the piston rod (orifice)? How can Bayesian statistics be applied to enhance the design of FVDs to account for such temperature variations likely encountered in offshore environments?

3-6 Months: Essential Literature Review

- Understanding critical literature: Over the next few months, I will delve deeper into essential readings and case studies, such as Black et al. (2003), to understand how Bayesian statistics have been applied in similar contexts. These studies will help shape my understanding of how to apply Bayesian statistics to the temperature problem within FVDs and how the results from a multi-physics simulation of FVDs can be integrated into such a study.

6-9 Months: Multi-Physics Preliminary Simulations

- Preliminary multi-physics simulations: I will start setting up preliminary simulations in COMSOL to model basic mechanical interactions within FVDs. These early simulations will focus on understanding how the dampers behave under simplified environmental loads, such as steady wind or wave forces. This will serve as the foundation for more complex simulations later.

- Presenting findings: At the nine-month progression review, I will present my preliminary findings, particularly highlighting the understanding of the essential literature (Black et al.). This internal review will be an opportunity to receive feedback from the panel examiners.

9-18 Months: Multi-Physics Simulation Development

- Developing detailed multi-physics simulations: During this period, I will create a comprehensive Finite Element (FE) model in COMSOL or ABAQUS, which will integrate fluid-temperature-structure interactions. These simulations will account for the combined effects of fluctuating temperatures, wind, and wave loads on FVD performance.

- Exploring temperature effects on damper fluid: I will focus on the temperature variations within the damper fluid, which can impact the output force of the FVDs. I will simulate the behaviour of FVDs for different damper geometries and environmental scenarios and evaluate how these variations affect the output force of FVDs.

- Cross-validating results: I will compare the results from the simulation with theoretical models and experimental results from the literature and examine the developed models for accuracy.

- Presenting findings: At the twenty-month progression review, I will present my findings from the multi-physics simulations of FVD behaviour. The highlight of the presentation will be the results from the simulations that demonstrate how environmental loads and temperature variations impact FVDs behaviour. This internal review will be an opportunity to receive feedback from my supervisors and peers.

19-31 Months: Bayesian Statistical Modelling and Updates

- Studying Bayesian statistics: I will study Bayesian statistics to understand how they can be applied to structural modelling and design in the presence of uncertainties.

- Applying Bayesian statistics: With simulation data in hand, I will begin applying Bayesian statistical methods to update the theoretical models for FVD performance. This will allow me to incorporate uncertainties associated with environmental loads of external temperature, and internal temperature change due to continuous loads of wave and wind and predict damper behaviour more accurately.

- Programming with Python: The above-mentioned application of Bayesian statistics will be conducted using Python. I will write the program for other people to easily understand. The program will be shared with other researchers for free in an open online platform such as Zenodo or GitHub after a careful review from my supervisors at the end stage of this PhD project. If time allows, I will use Jupyter Notebook and better explain my developed program of Bayesian statistics. This will allow my developed program to be studied and easily understood by other researchers. The outcome from the Jupyter Notebook will also be uploaded to the free online platform after a careful review from my supervisors at the end stage of this PhD project.

31-42 Months: Finalizing Research & Dissemination

- Deriving design factors: The goal during this phase will be to provide actionable insights for engineers. I will derive the design factors that can consider the temperature effect on the FVD output force based on the results of multi-physics simulations and Bayesian modelling to be used for the design of FVDs for offshore wind turbines.

- Writing my dissertation and journal submissions: I will focus on writing my PhD dissertation, detailing my methodologies, findings, and contributions to the field. In parallel, I will prepare at least 1-2 manuscripts for submission to high-impact academic journals, aiming to contribute to the broader academic community.

- Presenting research at conferences: I will also attend and present my findings at relevant conferences, ensuring that my research reaches both academic and industry audiences.

- Presenting findings: At the forty-month progression review, I will present my findings from the entire PhD project. This internal review will be an opportunity to receive feedback from my supervisors and peers and prepare for finalising my dissertation and viva voce examination.

#### 3. Key Challenges and Strategies for Success

Challenges:

- Learning multi-physics simulations and Bayesian statistics, which are currently unfamiliar subjects to me.

- Managing the autonomy required for PhD research while making progress on the research and achieving the expectations from the supervisory team and department/college/university requirements.

Strategies:

- I will hold regular meetings with my supervisory team, where I can seek guidance and feedback on both multi-physics simulations and statistical modelling.

- I will take advantage of workshops, tutorials, and seminars offered by Brunel University of London, particularly those focused on COMSOL, Python, and Bayesian statistics.

- Engaging with peers and post-doctoral researchers will be essential for collaborative problem-solving and motivation throughout my PhD journey.

#### 4. Career and Professional Development

In addition to my research, I will focus on building my professional profile:

- I will publish my research in academic journals and present my findings at key industry conferences, strengthening my academic position.

- I will seek networking opportunities with professionals in renewable energy and offshore engineering to explore future collaboration and employment opportunities.

- I will seek teaching and mentorship opportunities through some Brunel-endorsed programs, such as Brunel’s “Brilliant Scholar Tutor” program, helping me develop teaching and mentoring skills and contribute to the next generations in our local communities.

#### 5. Long-Term Vision

Post-PhD Career Path: My long-term goal is to transition into roles that bridge academia and industry, with a particular focus on renewable energy and sustainability. I aim to apply the knowledge gained from my PhD to improve the design of offshore structures and contribute to the advancement of renewable energy technologies.

Collaboration: I will continue building a global network of collaborators in civil engineering, renewable energy, and Bayesian statistics, allowing me to further my research impact and professional reach.

Bottom of Form